## Sheet1
Task | Start Date | # Days to Complete | Stop Date
Complete formal design specification | 2013-09-30 | 18 | 2013-10-18
Create user interface/editor interface appearance | 2013-10-18 | 7 | 2013-10-25
Develop variable declaration and method creation functionality | 2013-10-18 | 14 | 2013-11-01
Add core functionality: math, ifs, loops | 2013-11-01 | 24 | 2013-11-25
Add communication links with other modules | 2013-11-01 | 17 | 2013-11-18
Add data structure (array) functionality | 2013-11-18 | 7 | 2013-11-25
Drag and drop, GUI, improve appearance | 2013-11-18 | 23 | 2013-12-11
Final changes, fixes | 2013-12-11 | 5 | 2013-12-16
Formulas:
Stop Date = [Start Date]+C3
Stop Date = C7+[Start Date]