## Sheet1
Task | Start | Duration
Meet with Groups | 0 | 7
Create Design Document | 7 | 7
Create a Canvas | 14 | 14
Create interface with Sharing Framework | 28 | 28
Create interface with Visual Editor | 28 | 28
Get everything working together | 56 | 14